## Enhancements & Bug Fixes
Enhancements & Bug fixes - Request Information |  |  |  |  | Schedule Adherence / OnTime | [9 empty] | Effort (Person hours) | [8 empty] | Quality |  | Function Points
Id | App | Source | Req. Type | Brief Description / Name | Status | Assigned To | Received Date | Start Date | Estimated Closed | Actual Closed | On Time | Schedule Adherence | Month Year | Bug Fix Rate | Complexity | Estimated Effort | Analysis & Design Actual Effort | Build/Code + Self Test Actual Effort | Prevention & Training Actual Effort | Review & Testing Actual Effort | Rework Actual Effort | Other Effort | Actual Total Effort | # Internal Defects | # Escaped Defects (UAT or after) | Total
1 | App1 | SharePoint | Bug Fixes | Call_Center_Page_Mobfe | Closed | Angel Garza | 2015-04-01 | 2015-04-20 | 2015-04-25 | 2015-04-25 | Yes | 100% | Apr.2015 | 0 | Complex | 250 | 50 | 150 | 10 | 0 | 0 | 40 | 250 | 1 | 0 | NA
2 | App2 | Email | Major Enhancements | Sharepoint_SMS_Intake_Form_6 | Closed | Angel Garza | 2015-04-01 | 2015-04-20 | 2015-04-25 | 2015-04-25 | Yes | 100% | Apr.2015 | 0 | Medium | 420 | 20 | 340 | 0 | 10 | 20 | 30 | 420 | 1 | 1 | NA
3 | App3 | Subversion | Minor Enhancements | Sharepoint Task | Closed | Angel Garza | 2015-04-01 | 2015-04-20 | 2015-04-25 | 2015-04-26 | No | 99.8% | Apr.2015 | 0 | Simple | 100 | 50 | 20 | 10 | 0 | 0 | 20 | 100 | 1 | 0 | NA
4 | App3 | SharePoint | Minor Enhancements | Database Task | Closed | Angel Garza | 2015-08-01 | 2015-08-20 | 2015-08-25 | 2015-08-25 | Yes | 100% | Aug.2015 | 0 | Simple | 500 | 380 | 50 | 20 | 20 | 20 | 20 | 510 | 1 | 0 | NA
5 | App3 | Email | Minor Enhancements | Report for Client Task | Closed | Angel Garza | 2015-08-01 | 2015-08-20 | 2015-08-25 | 2015-08-25 | Yes | 100% | Aug.2015 | 0 | Simple | 300 | 250 | 10 | 10 | 10 | 10 | 10 | 300 | 1 | 0 | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
[14 empty] | 0 | [11 empty] | NA
Formulas:
Month Year = IF([Schedule Adherence / OnTime]<>"",IF([Schedule Adherence / OnTime]="Closed",CONCATENATE(IF([Actual Closed]="","",TEXT(IF([Actual Closed]="",TODAY(),[Actual Closed]),"MMM")),".",YEAR([Actual Closed])), "Pending"),"")
Note on W2: Quality Team: track UAT, Warranty, PM, CM activities
Note on Y2: Defects detected on: Requirements Analysis/Impact analysis, High Level Design, Detailed Design, Build/Unit Testing and Testing

## DT Prod Support
Production Support / Analysis & Research - Request Information | [7 empty] | On Time Delivery | [7 empty] | SLA Compliance | [5 empty] | Quality
Id | App | Source | Req. Type | Severity Type | Complexity | Brief Description | Assigned To | Status | Actual Effort (Hours) | Received Date / Time | Start Date/ Time | Resolved Date / Time | Actual Closed Date / Time | Estimated Close Date / Time | Month Year | Response Time (hrs) | SLA Response Time (hrs) | SLA Response Met? | TAT /Resolution Time (hrs) | SLA Resolution (hrs) | SLA Resolution Met? | Was Rejected/ Reopened? | Concatenate
1 | CashBalancing | esmart | Request Fulfillment | 4 - Low | Simple | Script executed correctly | Luis De Haro | Closed | 00:30 | 2015-09-01 12:59 | 2015-09-01 13:09 | 2015-09-01 13:29 | 2015-09-01 13:29 | 2015-09-01 14:59 | Sep.2015 | 0.16667 | 1 | Yes | 0.5 | 2 | Yes | No | Request Fulfillment - 4 - Low
2 | Vertex | esmart | Request Fulfillment | 4 - Low | Simple | Script executed correctly | Luis De Haro | Closed | 00:30 | 2015-09-01 13:08 | 2015-09-01 13:18 | 2015-09-01 13:38 | 2015-09-01 13:38 | 2015-09-01 15:08 | Sep.2015 | 0.16667 | 1 | Yes | 0.5 | 2 | Yes | No | Request Fulfillment - 4 - Low
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
-
Formulas:
Actual Closed Date / Time = [Received Date / Time]+[Actual Effort (Hours)]
Estimated Close Date / Time = IF([Received Date / Time]<>"",IF([SLA Resolution (hrs)]="NA","NA",[Received Date / Time]+TIME([SLA Resolution (hrs)],0,0)),"")
Month Year = IF([Actual Closed Date / Time]<>"",IF([On Time Delivery]="Closed",CONCATENATE(IF([Actual Closed Date / Time]="","",TEXT(IF([Actual Closed Date / Time]="",TODAY(),[Actual Closed Date / Time]),"MMM")),".",YEAR([Actual Closed Date / Time])), "Pending"),"")

## Catalog
Catalog for Delivery Trackers Use / Please Update the Catalogs Accordingly
Status | Source | Language | Conversion Factor | Complexity | Bug Fix Conv Factor | Enh Request Types | PS Request Types | Severity Types | Request - Severity (Concatenate) | SLA Response (Hrs) | SLA Resolution (hrs)
Cancelled | Email | C# | 25 | Simple | 0.8 | Minor Enhancements | Application and Batch Monitoring | 1 - Critical | Application and Batch Monitoring - 1 - Critical | NA | NA
Closed | esmart | HTML 4.0+ | 14 | Medium | 1 | Major Enhancements | Event Management | 2 - High | Application and Batch Monitoring - 2 - High | NA | NA
Resolved | IM | C# | 25 | Complex | 1.5 | Bug Fixes | Incident Management | 3 - Medium | Application and Batch Monitoring - 3 - Medium | NA | NA
In Progress | SharePoint | Informix | 40 |  |  |  | Problem Management | 4 - Low | Application and Batch Monitoring - 4 - Low | NA | NA
OnHold | SpotFire Server | Java | 53 |  |  |  | Request Fulfillment |  | Event Management - 1 - Critical | NA | NA
Open | Subversion | Oracle | 40 |  |  |  | Others |  | Event Management - 2 - High | NA | NA
Reopen | TeamSite | Pascal | 91 | [5 empty] | Event Management - 3 - Medium | NA | NA
Test | TFS | SQL | 13 | [5 empty] | Event Management - 4 - Low | NA | NA
| Maximo | Sybase | 40 | [5 empty] | Incident Management - 1 - Critical | 1 | 2
|  | T-SQL | 13 | [5 empty] | Incident Management - 2 - High | 1 | 2
|  | VB5 | 29 | [5 empty] | Incident Management - 3 - Medium | 1 | 2
|  | XML/XAML | 15 | [5 empty] | Incident Management - 4 - Low | 1 | 2
[9 empty] | Problem Management - 1 - Critical | 1 | 2
[9 empty] | Problem Management - 2 - High | 1 | 2
[9 empty] | Problem Management - 3 - Medium | 1 | 2
[9 empty] | Problem Management - 4 - Low | 1 | 2
[9 empty] | Request Fulfillment - 1 - Critical | 1 | 2
[9 empty] | Request Fulfillment - 2 - High | 1 | 2
[9 empty] | Request Fulfillment - 3 - Medium | 1 | 2
[9 empty] | Request Fulfillment - 4 - Low | 1 | 2
[9 empty] | Others - 1 - Critical | 1 | 2
[9 empty] | Others - 2 - High | 1 | 2
[9 empty] | Others - 3 - Medium | 1 | 2
[9 empty] | Others - 4 - Low | 1 | 2
[9 empty] | - 1 - Critical | 1 | 2
[9 empty] | - 2 - High | 1 | 2
[9 empty] | - 4 - Low | 1 | 2
Note on N3: Quality team: If SLA is not apllicable, Use "NA"
Note on O3: Quality team: If SLA is in terms of minutes use formula =MIN/60 to have value in hours

## Metrics Enhancements & Bug Fix
Major Enhancements / Minor Enhancements / Bug fixes / Delivery Tracker integrated: Metrics Dashboard FY2016
Project Code: | IPMCODE | Type: | Minor Enhancements |  |  | This is calculated automatically with the previous tab. | [6 empty] | Period: | H1FY16 |  | H2FY16
Framework Metric | Goal | APR.2015 | MAY.2015 | JUN.2015 | JUL.2015 | AUG.2015 | SEP.2015 | OCT.2015 | NOV.2015 | DEC.2015 | JAN.2016 | FEB.2016 | MAR.2016 | Average | Deviation | Average | Deviation
Estimation Variance | 10% | 0% | NA | NA | NA | 1.25% | NA | NA | NA | NA | NA | NA | NA | 0.625% | -93.75% | NA | NA
Productivity Minor | 75 | 0 | NA | NA | NA | 0 | NA | NA | NA | NA | NA | NA | NA | 0 | -100% | NA | NA
Productivity Bugfix | 85 | 0 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 0 | -100% | NA | NA
Productivity Major | 95 | 0 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 0 | -100% | NA | NA
On Time | 100% | 66.67% | NA | NA | NA | 100% | NA | NA | NA | NA | NA | NA | NA | 83.33% | -16.67% | NA | NA
On Quality | 0 | 1.2987 | NA | NA | NA | 0 | NA | NA | NA | NA | NA | NA | NA | 0.64935 | 64.94% | NA | NA
DIR | 2.5 | 1.3896 | NA | NA | NA | 0.24691 | NA | NA | NA | NA | NA | NA | NA | 0.81826 | -67.27% | NA | NA
Cost of Quality | 28% | 6.494% | NA | NA | NA | 11.11% | NA | NA | NA | NA | NA | NA | NA | 8.802% | -68.56% | NA | NA
Preventive/Corrective Actions
Remarks / Reasons for Deviation
April-
On Time

## Metrics PS
Production Support Metrics Dashboard Integrated with Delivery Tracker - FY2016
Project Code: | IPMCODE | Type: | Production Support |  |  | This is calculated automatically with the previous tab. | [6 empty] | Period: | H1FY16 |  | H2FY16
Framework Metric | Goal | APR.2015 | MAY.2015 | JUN.2015 | JUL.2015 | AUG.2015 | SEP.2015 | OCT.2015 | NOV.2015 | DEC.2015 | JAN.2015 | FEB.2015 | MAR.2015 | Average | Deviation | Average | Deviation
Productivity ABM | 10 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
Productivity EM | 20 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
Productivity IM | 10 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
Productivity PM | 20 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
Productivity RF | 30 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
Productivity Others | 20 | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
SLA Response | 95% | NA | NA | NA | NA | NA | 100% | NA | NA | NA | NA | NA | NA | 100% | 5.263% | NA | NA
SLA Resolution | 95% | NA | NA | NA | NA | NA | 100% | NA | NA | NA | NA | NA | NA | 100% | 5.263% | NA | NA
Reject/Reopened | 2% | NA | NA | NA | NA | NA | 0% | NA | NA | NA | NA | NA | NA | 0% | -100% | NA | NA
Preventive/Corrective Actions
Remarks / Reasons for Deviation
Note on D19: On Quality (Rejected/Reopened Tickets)